## Project Timeline
Week | Focus Area | Planned Tasks | Deliverables | Status
Week 1 | Planning & Database Design | Finalize project scope and requirements, prepare SRS, identify users and system modules, define functional and non-functional requirements, create use cases, design ER Diagram, database schema, and initial UI wireframes | SRS, Use Cases, ER Diagram, Database Design, UI Wireframes | In Progress
Week 2 | Backend Development | Create ASP.NET Core MVC project, configure MySQL and Entity Framework Core, implement database models and relationships, develop Student, Course, Enrollment, Attendance, and Grade modules, implement validation and CRUD operations, and prepare database scripts | Backend Modules, Database Scripts, CRUD Operations | Not Started
Week 3 | Frontend & UI Development | Design responsive user interface using HTML, CSS, Bootstrap, and JavaScript, develop forms and views, implement Admin Dashboard, integrate frontend with backend, add search, filtering, reports, and attendance status management including Present, Absent, and Excused | Completed UI, Admin Dashboard, Integrated System | Not Started
Week 4 | Testing & Documentation | Perform functional and database testing, fix bugs, improve code quality, review GitHub repository, prepare User Manual, Technical Documentation, database scripts, final presentation, and project demonstration | Tested Project, User Manual, Technical Documentation, Presentation, Final Demo | Not Started